## Version
CBS-SHWE_TC_BO_C# Convert Stored Procedure
Version: 1.0
Version history
Version | Maker | Revision Date | Checker | Approval Date | Document Changes
1 | NhiDY | 2024-12-31 |  |  | Create document

## Summary
Bàn giao test case
Ngày | 2025-01-02
Giờ | 18h00
Tổng số case | 210
Execute test case lần 1 theo ngày
Date Status | 2024-12-31 | 2025-01-02 | 2025-01-03 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09
Pass | 2 | 52 | 77 | 8 | 10 | 10 | 32
Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual execution | 2 | 52 | 77 | 8 | 10 | 10 | 32
Not yet execution | 208 | 156 | 79 | 71 | 61 | 51 | 19
Execute test case lần 2 theo ngày
Date Status | 2024-12-31 | 2025-01-02 | 2025-01-03 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09
Pass | 0 | 2 | 11 | 20 | 0 | 36 | 50
Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual execution | 0 | 2 | 11 | 20 | 0 | 36 | 50
Not yet execution | 210 | 208 | 197 | 177 | 177 | 141 | 91
Percent execute test case
Percent pass | 2024-12-31: 97.14%
Percent fail | bar: 2024-12-31
Percent block | bar: 2024-12-31
Percent pending | bar: 2024-12-31
Percent not completed | bar: 2024-12-31
Percent not run | 2024-12-31: 2.86%
Execute test case
Pass | 2024-12-31: 204
Fail | 2024-12-31: 0
Block | 2024-12-31: 0
Pending | 2024-12-31: 0
Not Completed | 2024-12-31: 0
Not run | 2024-12-31: 6

## Scenario Test
SUMMARY
Scenario ID | Scenario name | Pass | Fail | + | Block | Pending | Not Completed | - | Total | Percent pass | Percent fail | Percent not run | Percent block | Percent pending | Percent not completed | Remark
Customer
CTM_001 | SQL_INSERT_CTM: Add customer profile | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 0% | 0% | 0% | 0%
CTM_002 | SQL_UPDATE_CTM: Update customer profile | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 100% | 0% | 0% | 0% | 0% | 0%
CTM_003 | SQL_INSERT_MEDIA: Import media file | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 0% | 0% | 0% | 0%
CTM_004 | CTM_INSERT_CTM_API: OpenAPI add customer profile | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 0% | 0% | dùng chung step code SQL_INSERT_CTM
Deposit
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 100% | 0% | 0% | 0% | 0% | 0%
DPT_002 | DPT_VIEW_MODIFY_EXT_FIELD: View modify extension fields deposit account | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 0% | 0% | 0% | 0%
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 100% | 0% | 0% | 0% | 0% | 0%
DPT_004 | DPT_DELETE_ACCOUNTLINKAGE: Delete account linkage | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 0% | 0% | 0% | 0%
Admin
ADM_001 | ADM_REFRESH_BRANCH: Refresh bank | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 0% | 0%
ADM_002 | ADM_REFRESH_BRANCH_BY_USER: Refresh branch | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 0% | 0%
ADM_003 | ADM_CLOSE_BRANCH: Close branch | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 0% | 0% | 0% | 0%
ADM_004 | ADM_OPEN_BRANCH: Open branch | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 0% | 0% | 0% | 0%
ADM_005 | ADM_ADVANCED_SEARCH_ROLE_OF_USER: Role Profile - User - Assignment | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 0% | 0% | 0% | 0%
ADM_006 | ADM_SIMPLE_SEARCH_USER_ACCOUNT: Search common user profile | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 0% | 0% | 0% | 0%
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 0% | 0% | 0% | 0%
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 66.67% | 0% | 33.33% | 0% | 0% | 0%
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 66.67% | 0% | 33.33% | 0% | 0% | 0%
Payment
PMT_001 | PMT_SEARCH_SP_QUEUE_INWAR: Search common "Payment Queue for Inward" | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 0% | 0% | 0% | 0%
Accounting
ACT_001 | ACT_ACCHRT_SER_SIMPLE: Search common "Bank Account Definition" | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 0% | 0% | 0% | 0%
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 0% | 0% | 0% | 0%
Treasury
TRS_001 | TRS_SEARCH_ACCOUNT: Search common "Treasury account information" | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 0% | 0% | 0% | 0%
TRS_002 | TRS_VIEW_ACCOUNT: View "Treasury account information" | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 0% | 0% | 0% | 0%
Credit
CRD_001 | CRD_SEARCH_SP_CREDIT: Search common "Credit account information" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
CRD_002 | CRD_VIEW_CREDIT: View "Credit account information" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Foreign Exchange Rate
FXR_001 | FX_FXRATE_GETFXRATE: View "Foreign Exchange Rate" | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 0% | 0% | 0% | 0%
Total |  | 204 | 0 | 6 | 0 | 0 | 0 | 0 | 210 | 97.14% | 0% | 2.86% | 0% | 0% | 0%
Remark: Status of Test Scenario on section “Overall Status”:
- Passed = Test Scenario has been tested as planned and application works as expected result.
- Failed = Test Scenario has been tested as planned but application does not work as expected.
- Blocked = Test Scenario could not be tested as planned because there is an outstanding defect in related function area.
- Not Completed = Test Scenario has been tested as planned but not yet finished due to awaiting test result (ex: require EOD batch).
- No Run (+) = Test Scenario has not been tested as planned.
- Pending = Test Scenario will be tested after confirming about the business.
- Cancel (-) = Test Scenario could not be tested because of wrong condition, not suitable with the environment.

## TestCase
TEST CASES
Environment:
Scenario ID | Scenario name | Test case ID | Test condition ID | Condition | Expected Result | Result | Comments | Create date | Test lần 1 | Test lần 2 | Executor | Editor | Update date
CTM_001 | SQL_INSERT_CTM: Add customer profile
CTM_001 | SQL_INSERT_CTM: Add customer profile | CTM_001_001 |  | Add C1: Personal customer | Add successfully - Address - Extension fields - "LastModifyUserCode" get value is UserCode login Auto insert data into "Customer Linkage" Check data in the tables: - o9customer.dbo.SingleCustomer - o9customer.dbo.CustomerLinkage - o9customer.dbo.CustomerExtension - o9customer.dbo.CustomerAlias | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
CTM_001 | SQL_INSERT_CTM: Add customer profile | CTM_001_002 |  | Add C2: SME customer | Add successfully - Address - Extension fields - "LastModifyUserCode" get value is UserCode login Insert data into "Customer Group" Check data in the tables: - o9customer.dbo.SingleCustomer - o9customer.dbo.CustomerGroup - o9customer.dbo.CustomerExtension - o9customer.dbo.CustomerAlias | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
CTM_001 | SQL_INSERT_CTM: Add customer profile | CTM_001_003 |  | Add C3: Corporate customer | Add successfully - Address - Extension fields - "LastModifyUserCode" get value is UserCode login Insert data into "Customer Group" Check data in the tables: - o9customer.dbo.SingleCustomer - o9customer.dbo.CustomerGroup - o9customer.dbo.CustomerExtension - o9customer.dbo.CustomerAlias | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
CTM_001 | SQL_INSERT_CTM: Add customer profile | CTM_001_004 |  | Add C4: Institutional customer | Add successfully - Address - Extension fields - "LastModifyUserCode" get value is UserCode login Insert data into "Customer Group" Check data in the tables: - o9customer.dbo.SingleCustomer - o9customer.dbo.CustomerGroup - o9customer.dbo.CustomerExtension - o9customer.dbo.CustomerAlias | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
CTM_001 | SQL_INSERT_CTM: Add customer profile | CTM_001_005 |  | Update customer have extension fields with: - Reason For Other Economic Sector: empty - Reason For Other Business Type: empty - Referral Field: empty - Reason For Other Sub Economic Sector: empty - Reason For Other Occupation: empty - Reason For Other Paper Type: empty - Income: empty - Introducer: empty - Position: empty - Remark Field To Add: empty - Employer Name: empty - Fdi Info: empty - Tin Number: empty | Add successfully - Insert data into table "CustomerExtension" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
CTM_001 | SQL_INSERT_CTM: Add customer profile | CTM_001_006 |  | Add customer with address containing special characters | Add successfully - Address - Extension fields - "LastModifyUserCode" get value is UserCode login | Pass |  | 2025-01-02 | 2025-01-08 |  | NhiDY
CTM_001 | SQL_INSERT_CTM: Add customer profile | CTM_001_007 |  | Add customer with existing "Paper number" and "Paper type" | Add fail Error message "ERROR: Paper number existed" | Pass |  | 2025-01-02 |  |  | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_001 |  | Update C1: Personal customer - Status is "Pending to approve" | Modify successfully, NO need to approve - Address - Extension fields - "LastModifyUserCode" get UserCode of user login and make update - "UpdatedOnUtc" get date and time UTC | Pass |  | 2025-01-02 | 2025-01-06 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_002 |  | Update C1: Personal customer - Status is "Normal" or "Block" or "Decease Claim" or "Closed" | Modify successfully, need to approve - Address - Extension fields - "LastModifyUserCode" get UserCode of user login and make update - "UpdatedOnUtc" get date and time UTC - "LastUpdateDate" get real date | Pass |  | 2025-01-02 | 2025-01-06 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_003 |  | Update C2: SME customer - Status is "Pending to approve" | Modify successfully, NO need to approve - Address - Extension fields - "LastModifyUserCode" get UserCode of user login and make update - "UpdatedOnUtc" get date and time UTC - "LastUpdateDate" get working date | Pass |  | 2025-01-02 | 2025-01-06 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_004 |  | Update C2: SME customer - Status is "Normal" or "Block" or "Decease Claim" or "Closed" | Modify successfully, need to approve - Address - Extension fields - "LastModifyUserCode" get UserCode of user login and make update - "UpdatedOnUtc" get date and time UTC - "LastUpdateDate" get working date | Pass |  | 2025-01-02 | 2025-01-06 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_005 |  | Update C3: Corporate customer - Status is "Pending to approve" | Modify successfully, NO need to approve - Address - Extension fields - "LastModifyUserCode" get UserCode of user login and make update - "UpdatedOnUtc" get date and time UTC - "LastUpdateDate" get working date | Pass |  | 2025-01-02 | 2025-01-06 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_006 |  | Update C3: Corporate customer - Status is "Normal" or "Block" or "Decease Claim" or "Closed" | Modify successfully, need to approve - Address - Extension fields - "LastModifyUserCode" get UserCode of user login and make update - "UpdatedOnUtc" get date and time UTC - "LastUpdateDate" get working date | Pass |  | 2025-01-02 | 2025-01-06 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_007 |  | Update C4: Institutional customer - Status is "Pending to approve" | Modify successfully, NO need to approve - Address - Extension fields - "LastModifyUserCode" get UserCode of user login and make update - "UpdatedOnUtc" get date and time UTC - "LastUpdateDate" get working date | Pass |  | 2025-01-02 | 2025-01-06 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_008 |  | Update C4: Institutional customer - Status is "Normal" or "Block" or "Decease Claim" or "Closed" | Modify successfully, need to approve - Address - Extension fields - "LastModifyUserCode" get UserCode of user login and make update - "UpdatedOnUtc" get date and time UTC - "LastUpdateDate" get working date | Pass |  | 2025-01-02 | 2025-01-06 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_009 |  | Update customer have extension fields with: - Reason For Other Economic Sector: empty - Reason For Other Business Type: empty - Referral Field: empty - Reason For Other Sub Economic Sector: empty - Reason For Other Occupation: empty - Reason For Other Paper Type: empty - Income: empty - Introducer: empty - Position: empty - Remark Field To Add: empty - Employer Name: empty - Fdi Info: empty - Tin Number: empty | Modify successfully - Insert data into table "CustomerExtension" | Pass |  | 2025-01-02 | 2025-01-08 | 2025-01-08 | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_010 |  | Update customer have relation account information | Modify successfully | Pass |  | 2025-01-02 | 2025-01-08 |  | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_011 |  | Update customer with: - Status "Pending to approve" - Change paper number | Popup is showed 'Modify successfully | Pass |  | 2025-01-02 | 2025-01-08 |  | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_012 |  | Update customer with extension field change from "Other" to NOT "Other": - Reason For Other Economic Sector - Reason For Other Business Type - Reason For Other Sub Economic Sector - Reason For Other Occupation - Reason For Other Paper Type | Modify successfully - Data in "Other" field skipped, not clear data | Pass |  | 2025-01-02 | 2025-01-08 |  | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_013 |  | Update customer with address containing special characters | Modify successfully | Pass |  | 2025-01-02 | 2025-01-08 |  | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_014 |  | Update customer with: - "Is Restricted" is null | Modify successfully | Pass |  | 2025-01-02 | 2025-01-08 |  | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_015 |  | Update customer have NO extension fields with: - Reason For Other Economic Sector - Reason For Other Business Type - Referral Field - Reason For Other Sub Economic Sector - Reason For Other Occupation - Reason For Other Paper Type - Income - Introducer - Position - Remark Field To Add - Employer Name - Fdi Info - Tin Number Note: delete data in table "CustomerExtension" | Modify successfully | Pass |  | 2025-01-02 | 2025-01-08 |  | NhiDY
CTM_002 | SQL_UPDATE_CTM: Update customer profile | CTM_002_016 |  | Update customer with "Relation Deposit Information": - Deposit account have "Balance" is ******** | Modify successfully | Pass |  | 2025-01-02 | 2025-01-08 |  | NhiDY
CTM_003 | SQL_INSERT_MEDIA: Import media file
CTM_003 | SQL_INSERT_MEDIA: Import media file | CTM_003_001 |  | Import media file 2MB - PNG/JPG/PDF/Excel - Expired date is empty | Import successfully - Insert data is correct - o9customer.dbo.CustomerMediaStorage - o9cms.dbo.MediaUpload - o9cms.dbo.UserMedia | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
CTM_003 | SQL_INSERT_MEDIA: Import media file | CTM_003_002 |  | Import media file 2MB - PNG/JPG/PDF/Excel - Expired date is valid | Import successfully - Insert data is correct - o9customer.dbo.CustomerMediaStorage - o9cms.dbo.MediaUpload - o9cms.dbo.UserMedia | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
CTM_003 | SQL_INSERT_MEDIA: Import media file | CTM_003_003 |  | Import media file 5MB NOTE: update param Server "MEDIA_UPLOAD_MAX_SIZE" is "2" (mean: allow file with max size is 2MB) | Import fail | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
CTM_004 | CTM_INSERT_CTM_API: OpenAPI add customer profile
CTM_004 | CTM_INSERT_CTM_API: OpenAPI add customer profile | CTM_004_001 |  | Using openAPI for third parties | Add successfully - Address - Extension fields - "LastModifyUserCode" get value is UserCode login - Insert data into table "CustomerExtension" | Pass |  | 2025-01-02 | 2025-01-08 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_001 |  | Update current account - Status is "Pending to approve" | Modify successfully, NO need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_002 |  | Update current account - Status is "New" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_003 |  | Update current account - Status is "Normal" or "Block" or "Dormant" or "Closed" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_004 |  | Update saving account - Status is "Pending to approve" | Modify successfully, NO need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_005 |  | Update saving account - Status is "New" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_006 |  | Update saving account - Status is "Normal" or "Block" or "Dormant" or "Closed" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_007 |  | Update fixed deposit account - Status is "Pending to approve" | Modify successfully, NO need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_008 |  | Update fixed deposit account - Status is "New" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_009 |  | Update fixed deposit account - Status is "Normal" or "Block" or "Dormant" or "Closed" or "Maturity" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_010 |  | Update prepaid fixed deposit account - Status is "Pending to approve" | Modify successfully, NO need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_011 |  | Update prepaid fixed deposit account - Status is "New" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_012 |  | Update prepaid fixed deposit account - Status is "Normal" or "Block" or "Dormant" or "Closed" or "Maturity" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_013 |  | Update saving account with "IFC list" have information: + BasicBalance > 0.00 or + Paid > 0.00 or + BasicBalance > 0.00 NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "BasicBalance" and "Oustanding" and "Paid" are NOT update | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_014 |  | Update saving account with "IFC list" have information: + Oustanding = 0.00 + Paid > 0.00 + BasicBalance > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "BasicBalance" and "Oustanding" and "Paid" are NOT update - Can update "Margin Value" - Can update "IFC status" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_015 |  | Update saving account with "IFC list" have information: + Oustanding > 0.00 + Paid = 0.00 + BasicBalance > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "BasicBalance" and "Oustanding" and "Paid" are NOT update - Can update "Margin Value" - Can NOT update "IFC status", UI disable field | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_016 |  | Update saving account with "IFC list" have information: + Oustanding > 0.00 + Paid > 0.00 + BasicBalance > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "BasicBalance" and "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can NOT update "IFC status", UI disable field | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_017 |  | Update fixed deposit account with "IFC list" have information: + Oustanding > 0.00 or + Paid > 0.00 NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_018 |  | Update fixed deposit account with "IFC list" have information: + Oustanding = 0.00 + Paid > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can update "IFC status" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_019 |  | Update fixed deposit account with "IFC list" have information: + Oustanding > 0.00 + Paid = 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can NOT update "IFC status", UI disable field | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_020 |  | Update fixed deposit account with "IFC list" have information: + Oustanding > 0.00 + Paid > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can NOT update "IFC status", UI disable field | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_021 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount > 0.00 + Paid > 0.00 + IFC inused NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can NOT update "Margin Value" - Can NOT update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_022 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount > 0.00 + Paid > 0.00 + IFC inused Modify "Margin Value" of IFC | Modify failed - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can NOT update "Margin Value" - Can NOT update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_023 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount > 0.00 + Paid > 0.00 + IFC inused Modify "IFC status" of IFC | Modify failed - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can NOT update "Margin Value" - Can NOT update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_024 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount > 0.00 + Paid = 0.00 + IFC inused NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can NOT update "Margin Value" - Can NOT update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_025 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount > 0.00 + Paid = 0.00 + IFC inused Modify "Margin Value" of IFC | Modify failed - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can NOT update "Margin Value" - Can NOT update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_026 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount > 0.00 + Paid = 0.00 + IFC inused Modify "IFC status" of IFC | Modify failed - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can NOT update "Margin Value" - Can NOT update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_027 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount = 0.00 + Paid > 0.00 + IFC inused NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_028 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount = 0.00 + Paid > 0.00 + IFC inused Modify "Margin Value" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_029 |  | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount = 0.00 + Paid > 0.00 + IFC inused Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_030 |  | Update deposit account with "IFC list" have information: + Delete IFC item | Modify failed - NOT allow delete IFC in the list of items NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_031 |  | Update current account linked Overdraft account with "Balance information" have information: + "Current balance" is minus | Modify successfully, need to approve NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_032 |  | Update deposit account with "Balance information" have information: + "Available balance" is minus | Modify successfully, need to approve NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_033 |  | Update deposit account with "Balance information" have information: + "Current balance" is ******** + "Available balance" is ******** | Modify successfully, need to approve NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_034 |  | Update saving account with "IFC list" have information: + Add new IFC | Modify successfully, need to approve - Tab "IFC GLs Information" + GL account insert new row | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_035 |  | Update fixed deposit account with "IFC list" have information: + Add new IFC | Modify successfully, need to approve - Tab "IFC GLs Information" + GL account insert new row | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_036 |  | Update prepaid fixed deposit account with "IFC list" have information: + Add new IFC | Modify successfully, need to approve - Tab "IFC GLs Information" + GL account insert new row | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_037 |  | Update deposit have extension fields with: - Reason of Account Opening: empty - Relationship Manager: empty | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_038 |  | Update deposit have extension fields with: - Reason of Account Opening: have data - Relationship Manager: have data | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_039 |  | Update deposit account with: - "Is Restricted" is null | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_040 |  | Update curent account with: - Agent hub referral | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_041 |  | Update saving account with: - Agent hub referral | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_042 |  | Update fixed account with: - Agent hub referral - Rollover option - Rollover to catalogue | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_043 |  | Update prepaid fixed account with: - Agent hub referral - Rollover option - Rollover to catalogue | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_044 |  | Update deposit have NO extension fields with: - Reason of Account Opening - Relationship Manager Note: delete data in table "DepositAccountExtension" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_045 |  | Update deposit account have "Sweeping" information with: - Sweeping type: Both - Sweeping status: change from "Yes" to "No" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_046 |  | Update deposit account have "Sweeping" information with: - Sweeping type: Deficit - Sweeping status: change from "Yes" to "No" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_047 |  | Update deposit account have "Sweeping" information with: - Sweeping type: Surplus - Sweeping status: change from "Yes" to "No" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_048 |  | Update deposit account have "Sweeping" information with: - Sweeping status: from "No" to "Yes" | Not allow modify, UI disable check-box | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_049 |  | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - Sweeping type: Both - Deficit account status: <> Normal - Surplus account status: <> New and Normal | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_050 |  | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - Sweeping type: Deficit - Deficit account status: <> Normal | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_051 |  | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - Sweeping type: Surplus - Surplus account status: <> New and Normal | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_052 |  | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - To date (under sweeping) < working date | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_053 |  | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - To date (under sweeping) < from date | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_054 |  | Update deposit account have "Sweeping" information and linked with Overdraft account | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_001 | DPT_UPDATE_DEPOSIT: Modify deposit account | DPT_001_055 |  | Update deposit account with user not same branch | Not allow modify Error message "Only the branch holding the deposit account can be made" | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_002 | DPT_VIEW_MODIFY_EXT_FIELD: View modify extension fields deposit account
DPT_002 | DPT_VIEW_MODIFY_EXT_FIELD: View modify extension fields deposit account | DPT_002_001 |  | Update deposit account with extension fields: - Reason of Account Opening: empty - Relationship Manager: empty | View successfully - Have data under table "DepositAccountExtension" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_002 | DPT_VIEW_MODIFY_EXT_FIELD: View modify extension fields deposit account | DPT_002_002 |  | Update deposit account with extension fields: - Reason of Account Opening: have data - Relationship Manager: have data | View successfully - Have data under table "DepositAccountExtension" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_002 | DPT_VIEW_MODIFY_EXT_FIELD: View modify extension fields deposit account | DPT_002_003 |  | Update deposit account with extension fields: - Reason of Account Opening: text max length 250 - Relationship Manager: have data | View successfully - Have data under table "DepositAccountExtension" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_002 | DPT_VIEW_MODIFY_EXT_FIELD: View modify extension fields deposit account | DPT_002_004 |  | Update deposit have NO extension fields with: - Reason of Account Opening - Relationship Manager Note: delete data in table "DepositAccountExtension" | View successfully - Have data under table "DepositAccountExtension" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_001 | DPT_001_002 | Update current account - Status is "New" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_002 | DPT_001_003 | Update current account - Status is "Normal" or "Block" or "Dormant" or "Closed" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_003 | DPT_001_005 | Update saving account - Status is "New" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_004 | DPT_001_006 | Update saving account - Status is "Normal" or "Block" or "Dormant" or "Closed" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_005 | DPT_001_008 | Update fixed deposit account - Status is "New" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_006 | DPT_001_009 | Update fixed deposit account - Status is "Normal" or "Block" or "Dormant" or "Closed" or "Maturity" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_007 | DPT_001_011 | Update prepaid fixed deposit account - Status is "New" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_008 | DPT_001_012 | Update prepaid fixed deposit account - Status is "Normal" or "Block" or "Dormant" or "Closed" or "Maturity" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-08 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_009 | DPT_001_013 | Update saving account with "IFC list" have information: + BasicBalance > 0.00 or + Paid > 0.00 or + BasicBalance > 0.00 NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "BasicBalance" and "Oustanding" and "Paid" are NOT update | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_010 | DPT_001_014 | Update saving account with "IFC list" have information: + Oustanding = 0.00 + Paid > 0.00 + BasicBalance > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "BasicBalance" and "Oustanding" and "Paid" are NOT update - Can update "Margin Value" - Can update "IFC status" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_011 | DPT_001_015 | Update saving account with "IFC list" have information: + Oustanding > 0.00 + Paid = 0.00 + BasicBalance > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "BasicBalance" and "Oustanding" and "Paid" are NOT update - Can update "Margin Value" - Can NOT update "IFC status", UI disable field | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_012 | DPT_001_016 | Update saving account with "IFC list" have information: + Oustanding > 0.00 + Paid > 0.00 + BasicBalance > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "BasicBalance" and "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can NOT update "IFC status", UI disable field | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_013 | DPT_001_017 | Update fixed deposit account with "IFC list" have information: + Oustanding > 0.00 or + Paid > 0.00 NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_014 | DPT_001_018 | Update fixed deposit account with "IFC list" have information: + Oustanding = 0.00 + Paid > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can update "IFC status" | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_015 | DPT_001_019 | Update fixed deposit account with "IFC list" have information: + Oustanding > 0.00 + Paid = 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can NOT update "IFC status", UI disable field | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_016 | DPT_001_020 | Update fixed deposit account with "IFC list" have information: + Oustanding > 0.00 + Paid > 0.00 Modify "Margin Value" of IFC Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can NOT update "IFC status", UI disable field | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_017 | DPT_001_021 | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount > 0.00 + Paid > 0.00 + IFC inused NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can NOT update "Margin Value" - Can NOT update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_018 | DPT_001_024 | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount > 0.00 + Paid = 0.00 + IFC inused NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can NOT update "Margin Value" - Can NOT update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_019 | DPT_001_027 | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount = 0.00 + Paid > 0.00 + IFC inused NO modify IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_020 | DPT_001_028 | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount = 0.00 + Paid > 0.00 + IFC inused Modify "Margin Value" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_021 | DPT_001_029 | Update prepaid fixed deposit account with "IFC list" have information: + PrepaidAmount = 0.00 + Paid > 0.00 + IFC inused Modify "IFC status" of IFC | Modify successfully, need to approve - Tab "IFC list", IFC code with "Oustanding" and "Paid" is NOT update - Can update "Margin Value" - Can update "IFC status" NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_022 | DPT_001_031 | Update current account linked Overdraft account with "Balance information" have information: + "Current balance" is minus | Modify successfully, need to approve NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_023 | DPT_001_032 | Update deposit account with "Balance information" have information: + "Available balance" is minus | Modify successfully, need to approve NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_024 | DPT_001_033 | Update deposit account with "Balance information" have information: + "Current balance" is ******** + "Available balance" is ******** | Modify successfully, need to approve NOTE: Based on Production | Pass |  | 2025-01-02 | 2025-01-03 | 2025-01-09 | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_025 | DPT_001_034 | Update saving account with "IFC list" have information: + Add new IFC | Modify successfully, need to approve - Tab "IFC GLs Information" + GL account insert new row | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_026 | DPT_001_035 | Update fixed deposit account with "IFC list" have information: + Add new IFC | Modify successfully, need to approve - Tab "IFC GLs Information" + GL account insert new row | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_027 | DPT_001_036 | Update prepaid fixed deposit account with "IFC list" have information: + Add new IFC | Modify successfully, need to approve - Tab "IFC GLs Information" + GL account insert new row | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_028 | DPT_001_037 | Update deposit have extension fields with: - Reason of Account Opening: empty - Relationship Manager: empty | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_029 | DPT_001_038 | Update deposit have extension fields with: - Reason of Account Opening: have data - Relationship Manager: have data | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_030 | DPT_001_039 | Update deposit account with: - "Is Restricted" is null | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_031 | DPT_001_040 | Update curent account with: - Agent hub referral | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_032 | DPT_001_041 | Update saving account with: - Agent hub referral | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_033 | DPT_001_042 | Update fixed account with: - Agent hub referral - Rollover option - Rollover to catalogue | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_034 | DPT_001_043 | Update prepaid fixed account with: - Agent hub referral - Rollover option - Rollover to catalogue | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_035 | DPT_001_044 | Update deposit have NO extension fields with: - Reason of Account Opening - Relationship Manager Note: delete data in table "DepositAccountExtension" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-03 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_036 | DPT_001_045 | Update deposit account have "Sweeping" information with: - Sweeping type: Both - Sweeping status: change from "Yes" to "No" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_037 | DPT_001_046 | Update deposit account have "Sweeping" information with: - Sweeping type: Deficit - Sweeping status: change from "Yes" to "No" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_038 | DPT_001_047 | Update deposit account have "Sweeping" information with: - Sweeping type: Surplus - Sweeping status: change from "Yes" to "No" | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_039 | DPT_001_049 | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - Sweeping type: Both - Deficit account status: <> Normal - Surplus account status: <> New and Normal | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_040 | DPT_001_050 | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - Sweeping type: Deficit - Deficit account status: <> Normal | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_041 | DPT_001_051 | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - Sweeping type: Surplus - Surplus account status: <> New and Normal | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_042 | DPT_001_052 | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - To date (under sweeping) < working date | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_043 | DPT_001_053 | Update deposit account have "Sweeping" information with: - Sweeping status: Yes - To date (under sweeping) < from date | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_044 | DPT_001_054 | Update deposit account have "Sweeping" information and linked with Overdraft account | Modify successfully, need to approve | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_003 | DPT_APPROVE_MODIFY: Approve modify deposit account | DPT_003_045 |  | Approve modify deposit account with user not same branch | Not allow approve Error message "BranchOfUserNotAllowed: Only the branch holding the deposit account can be made" | Pass |  | 2025-01-02 | 2025-01-09 |  | NhiDY
DPT_004 | DPT_DELETE_ACCOUNTLINKAGE: Delete account linkage
DPT_004 | DPT_DELETE_ACCOUNTLINKAGE: Delete account linkage | DPT_004_001 |  | Delete account linkage: 1 master - 2 detail | System shows popup, choose "Yes" 2 rows data deleted, transaction successfully, follow master account | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
DPT_004 | DPT_DELETE_ACCOUNTLINKAGE: Delete account linkage | DPT_004_002 |  | Delete account linkage: 1 master - 1 detail | System shows popup, choose "Yes" 1 row data deleted, transaction successfully, follow master account | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
DPT_004 | DPT_DELETE_ACCOUNTLINKAGE: Delete account linkage | DPT_004_003 |  | Delete account linkage: 2 master - 1 detail, detele master 1 | System shows popup, choose "Yes" 1 row data deleted, transaction successfully, follow master account 1 | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
DPT_004 | DPT_DELETE_ACCOUNTLINKAGE: Delete account linkage | DPT_004_004 |  | Delete account linkage: 2 master - 1 detail, detele master 2 | System shows popup, choose "Yes" 1 row data deleted, transaction successfully, follow master account 2 | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
DPT_004 | DPT_DELETE_ACCOUNTLINKAGE: Delete account linkage | DPT_004_005 |  | Delete account linkage: 2 master - 1 detail, detele master 1 | System shows popup, choose "No" no row data delete | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_001 | ADM_REFRESH_BRANCH: Refresh bank
ADM_001 | ADM_REFRESH_BRANCH: Refresh bank | ADM_001_001 |  | - Go to screen "ADM-Bank Open/Close" - Click on "Refresh" | Transaction successfully All branches show information as below is correct: - Is Online - Branch Code - Name - Address - Phone | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_002 | ADM_REFRESH_BRANCH_BY_USER: Refresh branch
ADM_002 | ADM_REFRESH_BRANCH_BY_USER: Refresh branch | ADM_002_001 |  | - Go to screen "ADM-Branch Open/Close" - Click on "Refresh" | Transaction successfully Branch show information as below is correct: - Is Online - Branch Code - Name - Address - Phone | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_003 | ADM_CLOSE_BRANCH: Close branch
ADM_003 | ADM_CLOSE_BRANCH: Close branch | ADM_003_001 |  | - Go to screen "ADM-Bank Open/Close" - Choose branch want to close, branch don't have pending information - Click on "Close branch" icon | System shows popup approve, enter user and pass valid Close branch successfully | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_003 | ADM_CLOSE_BRANCH: Close branch | ADM_003_002 |  | - Go to screen "ADM-Branch Open/Close" - Branch don't have pending information - Click on "Close branch" icon | System shows popup approve, enter user and pass valid Close branch successfully | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_003 | ADM_CLOSE_BRANCH: Close branch | ADM_003_001 |  | - Go to screen "ADM-Bank Open/Close" - Choose branch want to close, branch don't have pending information - Click on "Close branch" icon | System shows popup approve, enter user and pass invalid Close branch fail | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_003 | ADM_CLOSE_BRANCH: Close branch | ADM_003_002 |  | - Go to screen "ADM-Branch Open/Close" - Branch don't have pending information - Click on "Close branch" icon | System shows popup approve, enter user and pass invalid Close branch fail | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_003 | ADM_CLOSE_BRANCH: Close branch | ADM_003_003 |  | - Go to screen "ADM-Bank Open/Close" - Choose branch want to close, branch have pending information - Click on "Close branch" icon | System shows popup approve, enter user and pass valid Close branch fail Show pending information CTM-Customer Profile CTM-Approve Profile Modification CTM-Approve Customer Linkage Modify CTM-Approve Customer relation management Modify DPT-Account Information DPT-Approve Account Modification Overdraft Account DPT-Approve Overdraft Contract Modification CRD-Account Information CRD-Approve Account Modification CRD-Product Limit CRD-Sub Product Limit MTG-Account Information ADM-Foreign Exchange Rate CTM-Customer media files ADM-Import Data Files Transaction pending | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_003 | ADM_CLOSE_BRANCH: Close branch | ADM_003_004 |  | - Go to screen "ADM-Branch Open/Close" - Branch have pending information - Click on "Close branch" icon | System shows popup approve, enter user and pass valid Close branch fail Show pending information CTM-Customer Profile CTM-Approve Profile Modification CTM-Approve Customer Linkage Modify CTM-Approve Customer relation management Modify DPT-Account Information DPT-Approve Account Modification Overdraft Account DPT-Approve Overdraft Contract Modification CRD-Account Information CRD-Approve Account Modification CRD-Product Limit CRD-Sub Product Limit MTG-Account Information ADM-Foreign Exchange Rate CTM-Customer media files ADM-Import Data Files Transaction pending | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_004 | ADM_OPEN_BRANCH: Open branch
ADM_004 | ADM_OPEN_BRANCH: Open branch | ADM_004_001 |  | - Go to screen "ADM-Bank Open/Close" - Choose branch want to open - Click on "Open branch" icon | System shows popup approve, enter user and pass valid Open branch successfully | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_004 | ADM_OPEN_BRANCH: Open branch | ADM_004_002 |  | - Go to screen "ADM-Branch Open/Close" - Click on "Open branch" icon | System shows popup approve, enter user and pass valid Open branch successfully | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_004 | ADM_OPEN_BRANCH: Open branch | ADM_004_003 |  | - Go to screen "ADM-Bank Open/Close" - Choose branch want to open - Click on "Open branch" icon | System shows popup approve, enter user and pass invalid Open branch fail | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_004 | ADM_OPEN_BRANCH: Open branch | ADM_004_004 |  | - Go to screen "ADM-Branch Open/Close" - Click on "Open branch" icon | System shows popup approve, enter user and pass invalid Open branch fail | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_005 | ADM_ADVANCED_SEARCH_ROLE_OF_USER: Role Profile - User - Assignment
ADM_005 | ADM_ADVANCED_SEARCH_ROLE_OF_USER: Role Profile - User - Assignment | ADM_005_001 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - User - Assignment" under "Shwebank" | Action successfully Show data is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_005 | ADM_ADVANCED_SEARCH_ROLE_OF_USER: Role Profile - User - Assignment | ADM_005_002 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - User - Assignment" under "Shwebank" - Choose "Select role" first time | Action successfully Show data is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_005 | ADM_ADVANCED_SEARCH_ROLE_OF_USER: Role Profile - User - Assignment | ADM_005_003 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - User - Assignment" under "Shwebank" - Choose "Select role" second time | Action successfully Show data is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-06 | NhiDY
ADM_006 | ADM_SIMPLE_SEARCH_USER_ACCOUNT: Search common user profile
ADM_006 | ADM_SIMPLE_SEARCH_USER_ACCOUNT: Search common user profile | ADM_006_001 |  | - Go to "ADM-User Profile-Search" screen - Search empty | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_006 | ADM_SIMPLE_SEARCH_USER_ACCOUNT: Search common user profile | ADM_006_002 |  | Search like follow value of column: - User Code - User Name - Login Name - Branch Name - Department Name - Email | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_006 | ADM_SIMPLE_SEARCH_USER_ACCOUNT: Search common user profile | ADM_006_003 |  | Search = follow value of column: - User Code - User Name - Login Name - Branch Name - Department Name - Email | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_006 | ADM_SIMPLE_SEARCH_USER_ACCOUNT: Search common user profile | ADM_006_004 |  | View random items | View successfully | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve | ADM_007_001 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - Invoke - Approve" under "Shwebank" | Action successfully Show data is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve | ADM_007_002 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - Invoke - Approve" under "Shwebank" - Choose "Menu name" first time - Choose the role want to update | Action successfully Show data is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve | ADM_007_003 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - Invoke - Approve" under "Shwebank" - Choose "Menu name" second time - Choose the role want to update | Action successfully Show data is correct | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve | ADM_007_004 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - Invoke - Approve" under "Shwebank" - Choose "Menu name" first time - Choose the role want to update - Un-check random action want to set no right | Action successfully Show data is correct The action showed for user | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve | ADM_007_005 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - Invoke - Approve" under "Shwebank" - Choose "Menu name" second time - Choose the role want to update - Un-check random action want to set no right | Action successfully Show data is correct The action showed for user | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve | ADM_007_006 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - Invoke - Approve" under "Shwebank" - Choose "Menu name" first time - Choose the role want to update - Check random action want to set right | Action successfully Show data is correct The action NOT showed for user | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_007 | ADM_UPDATE_LIST_USER_RIGHT: Role Profile - Invoke - Approve | ADM_007_007 |  | - Go to "ADM-Roles Profile" screen - Click on tab "Role Profile - Invoke - Approve" under "Shwebank" - Choose "Menu name" second time - Choose the role want to update - Check random action want to set right | Action successfully Show data is correct The action NOT showed for user | Pass |  | 2025-01-02 | 2025-01-02 | 2025-01-03 | NhiDY
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_001 |  | - Go to "FOF-Transaction Journal" screen - Search for mode "normal" - Search empty | Search successfully The data result is correct | Pass |  | 2025-01-02
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_002 |  | Search like follow value of column: - Tran Number - Tran Name - Account Number - Amount - Status - User Name - Branch Code | Search successfully The data result is correct | Pass |  | 2025-01-02
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_003 |  | Search = follow value of column: - Tran Number - Tran Name - Account Number - Amount - Status - User Name - Branch Code | Search successfully The data result is correct | Pass |  | 2025-01-02
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_004 |  | Search for transactions related to CASH | Search successfully The data result is correct, shows the "Cash" icon | Pass |  | 2025-01-02
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_005 |  | Search for transactions NOT related to CASH | Search successfully The data result is correct, NOT shows the "Cash" icon | Pass |  | 2025-01-02
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_006 |  | Search for transactions related to FOF-FX Transaction | Search successfully The data result is correct | Pass |  | 2025-01-02
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_007 |  | Search for transactions related to import data file | The data result not found | + |  | 2025-01-02
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_008 |  | Search for transactions follow user position | Search successfully The data result is correct | + |  | 2025-01-02
ADM_008 | SQL_SIMPLE_SEARCH_TRANSACTION_JOURNAL: Search common F8 | ADM_008_009 |  | View random items | View successfully | + |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_001 |  | - Go to "FOF-Transaction Journal" screen - Search for two mode "status" and "normal" - Search empty | Search successfully The data result is correct | Pass |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_002 |  | Search like follow value of fields: - Tran number - Tran name - Account number - Tran date - Tran time - Amount From - Amount To - Channel - Tran Type - User name - User approve - User Reject - Branch code - Approval reason | Search successfully The data result is correct | Pass |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_003 |  | Search = follow value of fields: - Tran number - Tran name - Account number - Tran date - Tran time - Amount From - Amount To - Channel - Tran Type - User name - User approve - User Reject - Branch code - Approval reason | Search successfully The data result is correct | Pass |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_004 |  | Search for transactions related to CASH | Search successfully The data result is correct, shows the "Cash" icon | Pass |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_005 |  | Search for transactions NOT related to CASH | Search successfully The data result is correct, NOT shows the "Cash" icon | Pass |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_006 |  | Search for transactions related to FOF-FX Transaction | Search successfully The data result is correct | Pass |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_007 |  | Search for transactions related to import data file | The data result not found | + |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_008 |  | Search for transactions follow user position | Search successfully The data result is correct | + |  | 2025-01-02
ADM_009 | SQL_ADVANCED_SEARCH_TRANSACTION_JOURNAL: Search advanced F8 | ADM_009_009 |  | View random items | View successfully | + |  | 2025-01-02
PMT_001 | PMT_SEARCH_SP_QUEUE_INWAR: Search common "Payment Queue for Inward"
PMT_001 | PMT_SEARCH_SP_QUEUE_INWAR: Search common "Payment Queue for Inward" | PMT_001_001 |  | - Go to "PMT-Payment Queue for Inward-Search" screen - Search empty | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
PMT_001 | PMT_SEARCH_SP_QUEUE_INWAR: Search common "Payment Queue for Inward" | PMT_001_002 |  | Search like follow value of column: - Message code - Ref no - Tran reference - Currency - Receive bank - Send bank - Receiver Id - Sender Id | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
PMT_001 | PMT_SEARCH_SP_QUEUE_INWAR: Search common "Payment Queue for Inward" | PMT_001_003 |  | Search = follow value of column: - Message code - Ref no - Tran reference - Currency - Receive bank - Send bank - Receiver Id - Sender Id | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
PMT_001 | PMT_SEARCH_SP_QUEUE_INWAR: Search common "Payment Queue for Inward" | PMT_001_004 |  | - Paging - Choose item per page - Jump to page | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
PMT_001 | PMT_SEARCH_SP_QUEUE_INWAR: Search common "Payment Queue for Inward" | PMT_001_004 |  | View random items | View successfully | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_001 | ACT_ACCHRT_SER_SIMPLE: Search common "Bank Account Definition"
ACT_001 | ACT_ACCHRT_SER_SIMPLE: Search common "Bank Account Definition" | ACT_001_001 |  | - Go to "ACT-Bank Account Definition-Search" screen - Search empty | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_001 | ACT_ACCHRT_SER_SIMPLE: Search common "Bank Account Definition" | ACT_001_002 |  | Search like follow value of column: - Account number - Currency - Account name | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_001 | ACT_ACCHRT_SER_SIMPLE: Search common "Bank Account Definition" | ACT_001_003 |  | Search = follow value of column: - Account number - Currency - Account name | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_001 | ACT_ACCHRT_SER_SIMPLE: Search common "Bank Account Definition" | ACT_001_004 | ACT_001_002 ACT_001_003 | - Paging - Choose item per page - Jump to page | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_001 | ACT_ACCHRT_SER_SIMPLE: Search common "Bank Account Definition" | ACT_001_005 |  | View random items | View successfully | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition"
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_001 |  | Insert GL account level 1 | Add successfully - Data insert into table "AccountChart" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_002 |  | Insert GL account level 2 | Add successfully - Data insert into table "AccountChart" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_003 |  | Insert GL account level 3 | Add successfully - Data insert into table "AccountChart" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_004 |  | Insert GL account level 4 | Add successfully - Data insert into table "AccountChart" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_005 |  | Insert GL account level 5 | Add successfully - Data insert into table "AccountChart" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_006 |  | Insert GL account level 6 | Add successfully - Data insert into table "AccountChart" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_007 |  | Insert GL account level 7 | Add successfully - Data insert into table "AccountChart" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_008 |  | Insert GL account level 8 | Add successfully - Data insert into table "AccountChart" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_009 |  | Insert GL account level 9 | Add successfully - Data insert into table "AccountChart" - Data insert into table "AccountBalance" | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_010 |  | Insert GL account level 9 existed | Add fail - Data not insert | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
ACT_002 | ACT_ACCHRT_INS: Add "Bank Account Definition" | ACT_002_011 |  | Insert GL account level 6, 7, 8 | Add fail - Data not insert | Pass |  | 2025-01-02 | 2025-01-02 |  | NhiDY
TRS_001 | TRS_SEARCH_ACCOUNT: Search common "Treasury account information"
TRS_001 | TRS_SEARCH_ACCOUNT: Search common "Treasury account information" | TRS_001_001 |  | Search empty | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
TRS_001 | TRS_SEARCH_ACCOUNT: Search common "Treasury account information" | TRS_001_002 |  | Search like follow value of column: - Account number - Branch code - Currency code - Account name - Counterparty code - Category code | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
TRS_001 | TRS_SEARCH_ACCOUNT: Search common "Treasury account information" | TRS_001_003 |  | Search = follow value of column: - Account number - Branch code - Currency code - Account name - Counterparty code - Category code | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
TRS_001 | TRS_SEARCH_ACCOUNT: Search common "Treasury account information" | TRS_001_004 | TRS_001_002 TRS_001_003 | - Paging - Choose item per page - Jump to page | Search successfully The data result is correct | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
TRS_001 | TRS_SEARCH_ACCOUNT: Search common "Treasury account information" | TRS_001_005 |  | View random items | View successfully | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
TRS_002 | TRS_VIEW_ACCOUNT: View "Treasury account information"
TRS_002 | TRS_VIEW_ACCOUNT: View "Treasury account information" | TRS_002_001 |  | View "MM Placement" account | View successfully - Data is correct - Tab "Settlement information" from "SettlementInformation" table: + On value date: Credit information + On maturity: Debit information | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
TRS_002 | TRS_VIEW_ACCOUNT: View "Treasury account information" | TRS_002_002 |  | View "MM Deposit" account | View successfully - Data is correct - Tab "Settlement information" from "SettlementInformation" table: + On value date: Debit information + On maturity: Credit information | Pass |  | 2025-01-02 | 2025-01-07 |  | NhiDY
CRD_001 | CRD_SEARCH_SP_CREDIT: Search common "Credit account information"
CRD_001 | CRD_SEARCH_SP_CREDIT: Search common "Credit account information" | CRD_001_001 | [5 empty] | 2025-01-02
CRD_001 | CRD_SEARCH_SP_CREDIT: Search common "Credit account information" | CRD_001_002 | [5 empty] | 2025-01-02
CRD_001 | CRD_SEARCH_SP_CREDIT: Search common "Credit account information" | CRD_001_003 | [5 empty] | 2025-01-02
CRD_001 | CRD_SEARCH_SP_CREDIT: Search common "Credit account information" | CRD_001_004 | [5 empty] | 2025-01-02
CRD_002 | CRD_VIEW_CREDIT: View "Credit account information"
CRD_002 | CRD_VIEW_CREDIT: View "Credit account information" | CRD_002_001 | [5 empty] | 2025-01-02
CRD_002 | CRD_VIEW_CREDIT: View "Credit account information" | CRD_002_001 | [5 empty] | 2025-01-02
CRD_002 | CRD_VIEW_CREDIT: View "Credit account information" | CRD_002_001 | [5 empty] | 2025-01-02
CRD_002 | CRD_VIEW_CREDIT: View "Credit account information" | CRD_002_001 | [5 empty] | 2025-01-02
FXR_001 | FX_FXRATE_GETFXRATE: View "Foreign Exchange Rate"
FXR_001 | FX_FXRATE_GETFXRATE: View "Foreign Exchange Rate" | FXR_001_001 |  | - Go to screen "ADM-Foreign Exchange Rate" | Transaction successfully Rate is showed, max "ValueDate", max "RateSequence" BK: Reference rate TB: Buying Transfer Rate TA: Selling Transfer Rate SB: Policy Rate CB: Buying Counter Rate CA: Selling Counter Rate | Pass |  | 2024-12-31 | 2024-12-31 | 2025-01-02 | NhiDY
FXR_001 | FX_FXRATE_GETFXRATE: View "Foreign Exchange Rate" | FXR_001_002 |  | - Enable new currency - Go to screen "ADM-Foreign Exchange Rate" | Transaction successfully Rate is showed, max "ValueDate", max "RateSequence" BK: Reference rate TB: Buying Transfer Rate TA: Selling Transfer Rate SB: Policy Rate CB: Buying Counter Rate CA: Selling Counter Rate All rate of new currency is 0.00 | Pass |  | 2024-12-31 | 2024-12-31 | 2025-01-02 | NhiDY

## UpdateData
Action | Update data | Update related table
|  | o9accounting |  | o9admin |  | o9cash |  | o9deposit
|  | Table name | Action | Table name | Action | Table name | Action | Table name | Action
Deposit money for deposit account (current, saving, fixed deposit) | Deposit account - Status: Normal (if prevoius status is New/ Dormant) - Increase Current balance, Available balance - Increase Deposit Amount, Week Credit, Month Credit, Quarter Credit, Semi - Annual Credit and Year Credit - BeginOfTenor = Working, EndOfTenor = Working date + tenor - LastChangeDormantToNormalDate (if previous status is Dormant) Deposit by cash - Increase Customer deposit, Total In, Closing balance of Cash flow Deposit by deposit - Decrease Current balance, Available balance - Increase Withdraw Amount, Week Debit, Month Debit, Quarter Debit, Semi - Annual Debit and Year Debit Deposit by GL - Decrease GL Balance | GLEntries | Insert new row | TransactionJournalDone | Insert new row | CashList | - CurrencyCode already existed: Update old row (update CurrentBalance) - CurrencyCode does not exist: Insert new row | DepositAccount | Update old row - DepositStatus (if prevoius status is New/ Dormant) - Psts - CurrentBalance, DepositAmount, WeekCredit, MonthCredit, QuarterCredit, SemiAnnualCredit, YearCredit - LastTransactionDate, UpdatedOnUtc - BeginOfTenor, EndOfTenor (if deposit type is Fixed Deposit) - LastChangeDormantToNormalDate (if previous status is Dormant) Update old row (if deposit by deposit) - Psts - CurrentBalance, WithdrawAmount, WeekDebit, MonthDebit, QuarterDebit, SemiAnnualDebit, YearDebit - LastTransactionDate, UpdatedOnUtc
|  | AccountBalance | Update old row (update Balance) | Transaction | Insert new row | CashStatement | - CashierCode, CurrencyCode, CashType and ValueDate already existed: Update old row (update CashAmount) - CashierCode, CurrencyCode, CashType and ValueDate do not exist: Insert new row | DepositStatement | Insert new row
|  | AccountStatement | Insert new row | TransactionDetail | Insert new row | CashTransaction | Insert new row | DepositHistory | Insert new row
|  | Transaction | Insert new row |  |  | GLEntries | Insert new row | DepositAccountTrans | Insert new row
|  | TransactionDetail | Insert new row |  |  | Transaction | Insert new row | GLEntries | Insert new row
[6 empty] | TransactionDetail | Insert new row | Transaction | Insert new row
[8 empty] | TransactionDetail | Insert new row
Withdraw money for deposit account (current, saving) | Deposit account - Decrease Current balance, Available balance - Increase Withdraw Amount, Week Debit, Month Debit, Quarter Debit, Semi - Annual Debit and Year Debit Withdraw by cash - Increase Customer withdrawal, Total Out, decrease Closing balance of Cash flow Withdraw by deposit - Increase Current balance, Available balance - Increase Deposit Amount, Week Credit, Month Credit, Quarter Credit, Semi - Annual Credit and Year Credit Withdraw by GL - Increase GL Balance | GLEntries | Insert new row | TransactionJournalDone | Insert new row | CashList | Update old row (update CurrentBalance) | DepositAccount | Update old row - DepositStatus (if prevoius status is New) - Psts - CurrentBalance, WithdrawAmount, WeekDebit, MonthDebit, QuarterDebit, SemiAnnualDebit, YearDebit - LastTransactionDate, UpdatedOnUtc - LastChangeDormantToNormalDate (if previous status is Dormant) Update old row (if withdraw by deposit) - DepositStatus (if prevoius status is New) - Psts - CurrentBalance, DepositAmount, WeekCredit, MonthCredit, QuarterCredit, SemiAnnualCredit, YearCredit - LastTransactionDate, UpdatedOnUtc
|  | AccountStatement | Insert new row | Transaction | Insert new row | CashStatement | - CashierCode, CurrencyCode, CashType and ValueDate already existed: Update old row (update CashAmount) - CashierCode, CurrencyCode, CashType and ValueDate do not exist: Insert new row | DepositStatement | Insert new row
|  | Transaction | Insert new row | TransactionDetail | Insert new row | CashTransaction | Insert new row | DepositHistory | Insert new row
|  | TransactionDetail | Insert new row |  |  | GLEntries | Insert new row | DepositAccountTrans | Insert new row
[6 empty] | Transaction | Insert new row | GLEntries | Insert new row
[6 empty] | TransactionDetail | Insert new row | Transaction | Insert new row
[8 empty] | TransactionDetail | Insert new row
Deposit money for prepaid fixed deposit | Fixed deposit account - Status: Normal (if prevoius status is New) - Increase Current balance, Available balance - Increase Deposit Amount, Week Credit, Month Credit, Quarter Credit, Semi - Annual Credit and Year Credit - BeginOfTenor = Working, EndOfTenor = Working date + tenor - Increase Interest prepaid Linkage account - Increase Current balance, Available balance - Increase Deposit Amount, Week Credit, Month Credit, Quarter Credit, Semi - Annual Credit and Year Credit Deposit by cash - Increase Customer deposit, Total In, Closing balance of Cash flow Deposit by deposit - Decrease Current balance, Available balance - Increase Withdraw Amount, Week Debit, Month Debit, Quarter Debit, Semi - Annual Debit and Year Debit | GLEntries | Insert new row | TransactionJournalDone | Insert new row | CashList | - CurrencyCode already existed: Update old row (update CurrentBalance) - CurrencyCode does not exist: Insert new row | DepositAccount | Update old row (Prepaid fixed deposit) - DepositStatus (if prevoius status is New) - Psts - CurrentBalance, DepositAmount, WeekCredit, MonthCredit, QuarterCredit, SemiAnnualCredit, YearCredit - LastTransactionDate, UpdatedOnUtc - BeginOfTenor, EndOfTenor (if deposit type is Fixed Deposit) - LastChangeDormantToNormalDate (if previous status is Dormant) Update old row (linkage account) - Psts - CurrentBalance, DepositAmount, WeekCredit, MonthCredit, QuarterCredit, SemiAnnualCredit, YearCredit - LastTransactionDate, UpdatedOnUtc Update old row (if deposit by deposit) - Psts - CurrentBalance, WithdrawAmount, WeekDebit, MonthDebit, QuarterDebit, SemiAnnualDebit, YearDebit - LastTransactionDate, UpdatedOnUtc
|  | AccountBalance | Update old row (update Balance) | Transaction | Insert new row | CashStatement | Insert new row | IFCBalance | Update old row (update PrepaidAmount)
|  | AccountStatement | Insert new row | TransactionDetail | Insert new row | CashTransaction | Insert new row | IFCBalanceDetail | Insert new row
|  | Transaction | Insert new row |  |  | GLEntries | Insert new row | DepositStatement | Insert new row
|  | TransactionDetail | Insert new row |  |  | Transaction | Insert new row | DepositHistory | Insert new row
[6 empty] | TransactionDetail | Insert new row | DepositAccountTrans | Insert new row
[8 empty] | DepositIFCBalanceTrans | Insert new row
[8 empty] | GLEntries | Insert new row
[8 empty] | Transaction | Insert new row
[8 empty] | TransactionDetail | Insert new row